PRODUCTION IMPLEMENTATION GUIDE

i-Elevate

From repository to a live, staff-facing Azure service

Including an on-campus IIS and SQL Server annex

—  A plain-English implementation and handover manual  —

Version 1.0  |  25 August 2026

Prepared from repository commit a4b0d0b9

Oldham College • Controlled handover copy

# Document control

| Field | Value |
| --- | --- |
| Purpose | Take the current i-Elevate repository through approval, Azure provisioning, identity setup, database preparation, release, pilot, go-live and ongoing support. |
| Primary audience | College IT, infrastructure, identity, database, information-governance, service-desk and application-owner teams. |
| Primary hosting model | Linux Azure App Service, Azure SQL Database, Microsoft Entra ID, Azure Storage, Key Vault, Application Insights and Log Analytics in UK South. |
| Alternative in Annex D | One Windows IIS website with an on-campus Microsoft SQL Server database. |
| Source baseline | Git commit a4b0d0b9f747d2e31e2cf1a4888132928a369812 on main, inspected 25 August 2026. |
| Review rule | Re-check Microsoft documentation, college policy, pricing, the release commit and all environment identifiers immediately before implementation. |

What this document is — and is not This is a repository-specific implementation runbook: what to do, why, what evidence to retain and where the relevant code lives. It does not replace college change, security, procurement, data-protection or identity approval.

Current state at preparation The resource group and Entra app registrations exist, but application resources, the final production redirect and tenant-wide consent are outstanding. Do not deploy the existing local ZIP: rebuild from a clean, approved commit or release tag.

## How to use this guide

- Sections 1–4 establish ownership, approvals and the release source. Accept them before provisioning.

- Identity, platform and database teams then complete Sections 5–10 in order. Do not open the service until sign-in, migrations and the first administrator are verified.

- Build and deploy through Sections 11–13; use Sections 14–19 and the annexes for live operation, recovery and handover.

# Contents

Select an entry in Word to jump to that section. Page numbers are deliberately omitted so the links remain correct if the college adds approval pages or local policy content.

1. Read this first

2. What is being deployed

3. Decisions, approvals and owners

4. Put the repository into college ownership

5. Prepare the deployment workstation

6. Finish Microsoft Entra configuration

7. Review Azure design, cost and security

8. Prepare deployment parameters

9. Validate and provision Azure

10. Prepare Azure SQL and the first administrator

11. Build and deploy the application

12. Complete DNS, HTTPS and sign-in

13. Pilot, acceptance and go-live

14. Operate the live service

15. Release updates safely

16. Rollback, recovery and incidents

17. Security and privacy operating controls

18. Troubleshooting guide

19. Formal handover pack

Annex A. Known environment record

Annex B. Azure command sheet

Annex C. Repository reference map

Annex D. On-campus IIS and SQL Server hosting

Annex E. Local development only

Annex F. Go-live sign-off checklist

Annex G. Plain-English glossary

Annex H. External references

# 1. Read this first

The quickest route to a reliable launch is to treat i-Elevate as a college service, not as a website somebody uploads. The source, staff data, Entra identities, Azure costs, database recovery and support rota all need named owners before go-live.

## The five rules that prevent most deployment failures

- Use the private, college-owned Git repository as the source of truth. A ZIP alone is not a maintainable handover.

- Build only from a clean, reviewed commit or release tag. Record the commit, tag, manifest and SHA-256 checksum in the change record.

- Apply database changes only through scripts/apply-database.ps1. Migrations are forward-only; never edit a migration already applied to production.

- Keep development authentication, LocalDB, demo/reset scripts and test accounts out of production. Production must use Microsoft Entra tokens.

- Do not open access to staff until sign-in, every role boundary, faculty/team scoping, reports, backups, alerts and recovery have been tested with evidence.

STOP condition Do not run the Bicep deployment merely to see what happens. It creates billable services. First obtain cost, security, data-protection and change approval, create a budget, identify the production owner and agree the network model.

## The intended result

Staff browse to one approved HTTPS address, sign in with their Oldham College Microsoft account and see only the records and functions allowed by their application role and faculty/team scope. The React interface and ASP.NET Core API are served from the same App Service address. Azure SQL holds the business data. The App Service uses its own managed identity—not a stored database password—to reach Azure SQL, Blob Storage and Key Vault.

## Out of scope unless separately approved

- General file uploads and evidence attachments. Storage policy, access control, file limits, retention and malware scanning must be designed first.

- Live outbound messaging. The supplied Azure configuration keeps messaging disabled and in test mode until the sender, credentials, test recipient and support owner are approved.

- A production LocalDB deployment. LocalDB is for a developer workstation only and is not a multi-user staff service.

- Automatic zero-downtime deployment on the Basic B1 plan. A staging slot requires Standard tier or better; the current starter deploys directly to the one production app.

Repository reference: DEPLOYMENT-START-HERE.md  •  HANDOVER.md  •  docs/deployment/v1-readiness.md

# 2. What is being deployed

## Application components

| Component | What it does | Repository location |
| --- | --- | --- |
| Web interface | React 19 and TypeScript staff interface, built by Vite and served as static files by the API. | apps/web |
| API | ASP.NET Core .NET 10 service enforcing identity, permissions, workflow rules, audit and reporting. | apps/api |
| Database | Azure SQL / SQL Server schemas, reference data, versioned forms, staff records, evidence, actions and audit history. | database |
| Infrastructure | Bicep definition for the Azure resource group and managed production services. | infrastructure/azure |
| Release tooling | Verification, packaging, migration, deployment, bootstrap and rollback scripts. | scripts |
| Automated checks | API, access-control, workflow, reporting and frontend build tests. | tests and .github/workflows |

## Azure request path

| From | To | Protection / purpose |
| --- | --- | --- |
| Staff browser | Microsoft Entra ID | College sign-in, MFA and Conditional Access; browser obtains an access token. |
| Staff browser | Linux App Service | HTTPS only. The same host serves the UI and /api/v1 endpoints. |
| App Service | Azure SQL Database | System-assigned managed identity with least-privilege database membership. |
| App Service | Blob Storage | Stores ASP.NET Core data-protection keys; OAuth/RBAC, no shared account key. |
| App Service | Key Vault | Wraps the data-protection key material; managed identity has Crypto User rights. |
| App Service | Application Insights | Operational telemetry and traces to a 30-day Log Analytics workspace. |

## Important application behaviour

- The API—not menu visibility—is the security boundary. Direct API calls outside a user's permission or organisational scope must fail.

- Microsoft Entra proves who the person is. Roles such as Admin, Teaching and Learning, Director, Head of Faculty, Programme Leader, QA Staff and Tutor are stored and enforced inside i-Elevate.

- A first-time tenant user can complete controlled self-onboarding, but the initial application role is staff. Administrative roles and managed-unit leadership must be assigned and checked by authorised administrators.

- The readiness endpoint /health/ready checks the database. /health/live confirms only that the application process is alive.

- Form templates and QA questions are versioned so later edits do not rewrite historical submissions.

Why Blob Storage and Key Vault exist They are not evidence-file storage in this release. They preserve and encrypt ASP.NET Core data-protection keys so protected application values remain readable after restarts and future scale-out.

Repository reference: apps/web/src/services/auth.ts  •  apps/api/src/TLQS.Api/Program.cs  •  infrastructure/azure/main.bicep

Microsoft/GitHub reference: Managed identities  •  ASP.NET Core key storage providers

# 3. Decisions, approvals and owners

## Name people, not just teams

| Responsibility | Minimum authority | Evidence to retain |
| --- | --- | --- |
| Business/product owner | Teaching and Learning owner authorised to accept the service | Signed acceptance and prioritised support route |
| Technical service owner | Accountable for availability, releases and incidents | Named primary and deputy |
| GitHub owner | College organisation owner/repository administrator | Private repository ownership and recovery access |
| Azure platform | Subscription Owner or Contributor plus role-assignment rights | Approved subscription, region, cost centre and deployment record |
| Identity | Application/Cloud Application Administrator and consent authority | App ownership, permission review, redirect URIs, consent and CA evidence |
| Database | Entra SQL administrator and recovery deputy | Migration log, permissions, backup policy and restore test |
| Information governance | Data owner / DPO-approved delegate | DPIA or equivalent assessment, retention and privacy decision |
| Service desk | Monitored support queue and escalation manager | Runbook, alert destination, SLAs and contact details |

## Decisions that must be written down

☐  Final staff-facing hostname, for example https://ielevate.oldham.ac.uk. Do not guess it in the Entra portal.

☐  Whether the public Azure endpoint design meets college policy, or whether VNet integration/private endpoints are mandatory before launch.

☐  App Service tier and instance count; whether a staging slot and zero-downtime swap are required.

☐  Azure SQL short-term retention, backup redundancy, long-term retention and tested recovery objectives (RPO/RTO).

☐  Who may sign in: all tenant users with application-side checks, or an Entra-assigned staff group only.

☐  Whether the supplied official curriculum staff seed is approved and current. If not, exclude it and load approved staff/organisation data later.

☐  Pilot group, acceptance owner, planned launch window, communications, support cover and rollback threshold.

☐  Retention and access-review frequency for staff records, evidence, audit data, exports and operational logs.

## Recommended release gates

| Gate | Must be true before proceeding |
| --- | --- |
| G0 — Ownership | Repository, subscription, Entra apps, database, data and support each have a primary and deputy owner. |
| G1 — Design | Security, network, cost, region, sizing, recovery and data-protection decisions are accepted. |
| G2 — Build | Clean commit/tag passes CI, dependency audits and release verification; package checksum recorded. |
| G3 — Platform | Bicep deployment validated/previewed, resources provisioned and outputs recorded. |
| G4 — Data | Migrations complete, managed identity works, backup/restore policy set and bootstrap admin verified. |
| G5 — Acceptance | Role/scoping, functional, reporting, accessibility, security and recovery tests are signed off. |
| G6 — Launch | DNS/TLS, Entra consent/assignment, monitoring, service desk and communications are live. |

# 4. Put the repository into college ownership

The current remote points to a personal GitHub account. Transfer it to an approved private college organisation before production. A transfer preserves issues, pull requests and Git history; confirm the old URL redirects and update local remotes afterwards.

## Transfer and protect

- Create or identify the approved Oldham College GitHub organisation and nominate at least two permanent organisation owners.

- In the current repository's GitHub Settings, use General → Danger Zone → Transfer ownership. Enter the approved organisation and confirm the repository name.

- Confirm the transferred repository is Private. Remove obsolete personal collaborators and assign college teams using least privilege.

- Update each maintainer's local remote with git remote set-url origin https://github.com/<college-org>/<repository>.git.

- Create an active ruleset for main: require a pull request, at least one independent approval, resolved conversations and the API/Web CI status checks; block force-pushes and deletion.

- Enable the organisation's approved Dependabot, secret-scanning, code-scanning and audit-log controls. Do not put passwords in GitHub variables.

- Create a production GitHub Environment if future automated deployment is introduced; require human approval and keep deployment credentials in approved secrets or, preferably, use workload identity federation.

## Repository variables used by the existing release workflow

| Variable | Value / rule |
| --- | --- |
| ENTRA_TENANT_ID | 2ff33ca4-e942-419c-b5ca-e224a5167498 |
| ENTRA_API_CLIENT_ID | f6d35a24-dc89-40b0-819a-69400ed2491d |
| ENTRA_SPA_CLIENT_ID | 40b00b7a-32b3-4a89-bac0-f016fd431d95 |
| ENTRA_API_SCOPE | api://f6d35a24-dc89-40b0-819a-69400ed2491d/access_as_user |

Identifiers are not passwords The four values above are non-secret identifiers required at build time. GitHub variables are appropriate. SQL passwords, client secrets, tokens, certificates, production exports and connection credentials are not variables and must never be committed or printed in workflow logs.

## Create the first approved tag

git status --short
git pull --ff-only
git tag -a v1.0.0 -m "i-Elevate production release v1.0.0"
git push origin main
git push origin v1.0.0

Only tag after the branch is clean, CI passes, the code is accepted and the exact commit is recorded. Use the college's release naming policy if it differs.

Repository reference: .github/workflows/ci.yml  •  .github/workflows/release-azure.yml  •  HANDOVER.md

Microsoft/GitHub reference: Move work to an organisation  •  Repository rulesets  •  GitHub Actions variables

# 5. Prepare the deployment workstation

Use a managed Windows workstation or controlled build runner. The operator must be able to access the college tenant, subscription, GitHub repository and—temporarily—the Azure SQL public endpoint if the starter network design is used.

## Required tools

| Tool | Repository requirement | Check |
| --- | --- | --- |
| Git | Current supported client | git --version |
| PowerShell | PowerShell 7 recommended; Windows PowerShell scripts are supported where stated | $PSVersionTable.PSVersion |
| .NET SDK | 10.0.300 or compatible latest feature band | dotnet --info |
| Node.js | 24 | node --version |
| npm | Bundled with approved Node installation | npm --version |
| Azure CLI | Current supported version with Bicep | az version; az bicep version |
| sqlcmd | Microsoft SQL command-line tools with Entra support | sqlcmd -? |
| Optional SSMS | Current supported SQL Server Management Studio | Use Microsoft Entra authentication |

## Prepare a clean checkout

git clone https://github.com/<college-org>/<repository>.git
Set-Location .\<repository>
git fetch --tags --prune
git checkout v1.0.0
git status --short

The final command must return no changed or untracked files. Do not use -AllowDirty for a production release.

## Check the Azure context before every Azure command

az login --tenant 2ff33ca4-e942-419c-b5ca-e224a5167498
az account set --subscription acd523b9-54eb-4bbe-8776-fb761860c362
az account show --query "{tenant:tenantId,subscription:id,name:name,user:user.name}" -o table

Read the displayed account Do not assume az login selected the correct tenant or subscription. Stop if either GUID differs from the approved environment record, or if the displayed operator is not the authorised deployment identity.

## Confirm the App Service runtime string before provisioning

az webapp list-runtimes --os linux --runtime dotnet --support supported -o table

The current Bicep template uses DOTNETCORE|10.0. Confirm that Azure still lists the .NET 10 Linux runtime in UK South. If Microsoft changes the accepted string, update and review the Bicep template before deployment—do not improvise directly in production.

Repository reference: global.json  •  Directory.Packages.props  •  apps/web/package.json  •  scripts/check-prerequisites.ps1

Microsoft/GitHub reference: Bicep with Azure CLI  •  Configure ASP.NET Core on App Service

# 6. Finish Microsoft Entra configuration

i-Elevate deliberately uses two single-tenant app registrations: one identifies the protected API and exposes a delegated scope; the second identifies the React single-page application (SPA) used in the browser. Neither registration needs a client secret for this design.

## Known registrations

| Registration | Known ID | Purpose |
| --- | --- | --- |
| i-Elevate API | f6d35a24-dc89-40b0-819a-69400ed2491d | Validates Oldham College user tokens and exposes access_as_user. |
| i-Elevate Web | 40b00b7a-32b3-4a89-bac0-f016fd431d95 | Browser SPA requests the API's delegated scope. |
| Tenant | 2ff33ca4-e942-419c-b5ca-e224a5167498 | Accounts in this organisational directory only. |

## Check the API registration

☐  Supported account type is Accounts in this organisational directory only.

☐  Application ID URI is api://f6d35a24-dc89-40b0-819a-69400ed2491d.

☐  Expose an API contains an enabled delegated scope named access_as_user.

☐  The full scope is api://f6d35a24-dc89-40b0-819a-69400ed2491d/access_as_user.

☐  The i-Elevate Web client is listed as an authorised client application if the identity team uses pre-authorisation.

☐  At least two permanent college owners are assigned to both the app registration and its enterprise application.

## Check the Web SPA registration

☐  Supported account type is single tenant.

☐  Authentication contains a Single-page application platform—not Web—with the exact final HTTPS origin, for example https://ielevate.oldham.ac.uk.

☐  Do not use a wildcard. Remove obsolete localhost or temporary production redirects after the launch and support model no longer needs them.

☐  API permissions contains the i-Elevate API delegated access_as_user scope. It does not require Microsoft Graph permissions for current application behaviour.

☐  Implicit grant checkboxes remain off; MSAL browser uses the modern SPA flow.

## Grant administrator consent

- An authorised identity administrator opens Microsoft Entra admin centre → App registrations → i-Elevate Web → API permissions.

- They review the exact requested permission. It should be the college-owned i-Elevate API access_as_user delegated scope, not broad Microsoft Graph access.

- Select Grant admin consent for the Oldham College tenant and confirm. If the button is disabled, the signed-in account lacks the required Entra directory role; escalate rather than creating another registration.

- Record who granted consent, when, the tenant, application IDs and the permission in the controlled change record.

Who can grant consent Microsoft documents Cloud Application Administrator or Application Administrator as sufficient for permissions other than Microsoft Graph application roles; Privileged Role Administrator can grant any API permission. Use the college's privileged-access process and least-privilege role activation.

## Decide who can sign in

The application enforces its own roles and scopes, but the Entra enterprise application can add an outer gate. For a staff system, the recommended pattern is Assignment required = Yes and assignment of an approved staff security group plus support/admin break-glass users. This prevents an arbitrary tenant account reaching self-onboarding. Test group licensing and nested-group behaviour before relying on group assignment.

## Conditional Access

- Apply existing college MFA, device-compliance, sign-in-risk and location policies to the enterprise application through the identity team.

- Start new policies in report-only mode, test administrators and ordinary staff, and preserve emergency-access accounts according to college policy.

- Do not duplicate authentication inside the application or enable App Service Easy Auth without a reviewed design change; the API already validates Entra JWTs.

Repository reference: apps/web/src/services/auth.ts  •  apps/api/src/TLQS.Api/Program.cs  •  apps/api/src/TLQS.Api/appsettings.json

Microsoft/GitHub reference: SPA redirect URI guidance  •  Expose API scopes  •  Grant tenant-wide consent  •  Restrict an app to assigned users

# 7. Review Azure design, cost and security

The supplied infrastructure is a deliberate starter: compact, understandable and suitable for a controlled pilot. It is not a substitute for the college platform team's security architecture. Review every item below before accepting it for a staff-wide service.

## Resources created by the Bicep template

| Resource | Starter setting | Operational meaning |
| --- | --- | --- |
| Resource group | rg-ielevate-prod-uks, UK South | Single tagged boundary for the production service. |
| App Service plan | Linux Basic B1, 1 instance | Always On; no staging slot; single worker. |
| Web App | .NET 10 Linux, HTTPS, TLS 1.2, HTTP/2 | Serves UI and API; system-assigned managed identity; /health/ready. |
| Azure SQL | General Purpose serverless Gen5, 0.5–2 vCores | Database ielevate; 60-minute auto-pause configured. |
| Storage | Standard LRS StorageV2 | Private blob container for data-protection keys; 30-day soft delete. |
| Key Vault | Standard, RBAC, purge protection | RSA key wraps data-protection keys; 90-day soft delete. |
| Application Insights | Workspace based | Application telemetry. |
| Log Analytics | PerGB2018, 30 days | Operational log retention. |

## What the starter secures

- HTTPS only, TLS 1.2 minimum, FTPS disabled and remote debugging disabled.

- No database credential in the application connection string; Azure SQL uses Active Directory Default and the App Service managed identity.

- Blob public access and Storage shared-key access disabled; OAuth/RBAC used instead.

- Key Vault RBAC, soft delete and purge protection enabled.

- The app receives Storage Blob Data Contributor and Key Vault Crypto User—no broad Owner role.

- Development user authentication disabled in Production; messaging disabled and test mode enabled.

## Security decisions still required

| Current starter | Risk / limitation | Recommended production decision |
| --- | --- | --- |
| Public App Service endpoint | UI shell and health endpoints are internet reachable; application data still requires Entra. | Choose public-with-Entra/CA and access restrictions, or App Service private endpoint with college VPN/ExpressRoute and private DNS. |
| SQL AllowAzureServices 0.0.0.0 | Allows connection attempts from Azure resources in other tenants; SQL authentication/authorisation still applies. | Prefer App Service VNet integration plus SQL private endpoint, then disable public access. At minimum document and review the exception. |
| Storage and Key Vault default network allow | RBAC protects data but the public endpoints are reachable. | Use private endpoints/firewalls if required by college policy; test App Service DNS and outbound routing before disabling public access. |
| One B1 instance | No worker redundancy and direct deployment restart/brief interruption. | For broad use, consider Standard or higher, two instances and a staging slot after measuring costs. |
| SQL local backup redundancy | A local regional storage failure has less protection than zone/geo options. | Set redundancy and long-term retention to the agreed recovery and data-residency policy. |
| 30-day telemetry | May be too short or too long for support/privacy policy. | Agree retention, sampling and redaction; never log tokens, request bodies or staff narrative. |

Serverless cost caveat The App Service health check calls /health/ready every minute and that endpoint opens a database connection. This traffic can prevent Azure SQL from becoming idle enough to auto-pause. Treat auto-pause savings as unproven and verify actual behaviour and cost after deployment.

## Cost control before creation

- Open Azure Pricing Calculator and model the exact UK South App Service, Azure SQL compute/storage/backups, Log Analytics ingestion, Application Insights, Storage, Key Vault and any private endpoints/VNet services.

- Assign the approved cost centre and owners using tags or college policy. The Bicep template already tags application, environment, managedBy and dataClassification.

- Create a monthly budget at resource-group or subscription scope with actual and forecast thresholds routed to at least the service owner and finance/platform owner.

- Understand that a budget sends alerts; it does not automatically stop the service or stop charges.

- After acceptance, consider a CanNotDelete lock on critical production resources or the resource group. Test deployment procedures because locks can block legitimate changes.

Repository reference: infrastructure/azure/main.bicep  •  infrastructure/azure/subscription.bicep

Microsoft/GitHub reference: SQL firewall warning  •  App Service private endpoints  •  Storage network security  •  Secure Key Vault  •  Azure budgets

# 8. Prepare deployment parameters

The repository contains an example parameter file. Copy it to an approved restricted location outside the repository. The completed file contains a SQL break-glass password and must not be placed in Git, OneDrive sharing links, email, Teams chat, tickets or release notes.

## Parameter-by-parameter

| Parameter | Recommended / known value | Owner or note |
| --- | --- | --- |
| resourceGroupName | rg-ielevate-prod-uks | Already exists empty; Bicep can target it. |
| location | uksouth | Confirm region and data policy. |
| namePrefix | ielevate-oldham | Lowercase, 3–18 characters; Azure adds unique suffixes. |
| environmentName | prod | Allowed: dev, test, prod. |
| entraTenantId | 2ff33ca4-e942-419c-b5ca-e224a5167498 | Oldham College tenant; verify in portal. |
| entraApiAudience | f6d35a24-dc89-40b0-819a-69400ed2491d | API app client ID. |
| sqlEntraAdministratorLogin | Named DBA user or, after template enhancement, approved group | Must be able to connect and create external users. |
| sqlEntraAdministratorObjectId | That Entra principal's object ID | Object ID—not application/client ID. |
| sqlAdministratorLogin | ielevatesqladmin | Break-glass SQL login; application does not use it. |
| sqlAdministratorPassword | Strong unique value from approved password process | Secure parameter; retain in approved vault and rotate. |
| deploymentIpAddress | Operator workstation's current public IPv4 | Temporary SQL migration rule; remove after setup. |
| appServiceSkuName / Tier | B1 / Basic initially | Revisit if slots/redundancy required. |
| sqlMaximumVcores | 2 | Measure after pilot. |
| sqlAutoPauseDelayMinutes | 60 | May not pause because readiness health checks query SQL. |

## Create the controlled copy

Copy-Item .\infrastructure\azure\subscription.parameters.example.json `
  C:\Secure\i-elevate\subscription.parameters.prod.json

Restrict the folder to the authorised deployment operator and platform administrators. Replace angle-bracket placeholders. Have a second person review tenant, subscription, Entra IDs, SQL administrator object ID, region and temporary IP.

Safer secret entry Where the college's tooling allows it, inject the secure SQL parameter from the approved secret vault or a protected deployment pipeline. If a temporary JSON parameter file must contain it, restrict the file, use it only for the deployment, then remove it according to the college's secure-media procedure. The example in the repository must remain placeholder-only.

Repository reference: infrastructure/azure/subscription.parameters.example.json

# 9. Validate and provision Azure

This phase creates the billable platform. Use a named subscription-level deployment so its inputs, outputs and activity log can be audited.

## Compile and validate before creation

az bicep build --file .\infrastructure\azure\subscription.bicep `
  --outfile "$env:TEMP\ielevate-subscription.json"

az deployment sub validate `
  --name ielevate-prod-validate-20260825 `
  --location uksouth `
  --template-file .\infrastructure\azure\subscription.bicep `
  --parameters "@C:\Secure\i-elevate\subscription.parameters.prod.json"

## Preview the change

az deployment sub what-if `
  --name ielevate-prod-whatif-20260825 `
  --location uksouth `
  --template-file .\infrastructure\azure\subscription.bicep `
  --parameters "@C:\Secure\i-elevate\subscription.parameters.prod.json"

Save the what-if output in the change record. A reviewer should expect the App Service plan/app, Azure SQL server/database/firewall rules, Storage/container, Key Vault/key, managed-identity RBAC, Application Insights and Log Analytics resources. Stop on unexplained deletes, region changes, tier changes or broad roles.

## Create the platform

$DeploymentName = "ielevate-prod-20260825"
az deployment sub create `
  --name $DeploymentName `
  --location uksouth `
  --template-file .\infrastructure\azure\subscription.bicep `
  --parameters "@C:\Secure\i-elevate\subscription.parameters.prod.json"

## Capture the outputs

az deployment sub show `
  --name $DeploymentName `
  --query properties.outputs `
  --output json

| Output | Use it for |
| --- | --- |
| applicationUrl | Initial Azure HTTPS address and temporary SPA redirect. |
| resourceGroupName | All later Azure CLI commands. |
| webAppName | ZIP deployment, settings, logs and managed-identity display name. |
| webAppManagedIdentityObjectId | Audit/RBAC confirmation; keep in the environment record. |
| sqlServerFullyQualifiedDomainName | Migration and runtime verification. |
| sqlDatabaseName | Expected value ielevate. |

## Post-provision platform checks

☐  Every resource is in rg-ielevate-prod-uks and UK South unless an approved exception exists.

☐  Web App Identity shows System assigned = On.

☐  Storage role assignment is Storage Blob Data Contributor for the web app identity only.

☐  Key Vault role assignment is Key Vault Crypto User for the web app identity only.

☐  Web App configuration contains Production environment, expected Entra IDs, managed-identity SQL string and both data-protection URIs; values are not shown in tickets/screenshots unnecessarily.

☐  HTTPS Only, TLS minimum 1.2, FTPS disabled, remote debugging off, Always On and /health/ready are configured.

☐  Budget and alert recipients are configured immediately; do not wait for the first invoice.

Repository reference: infrastructure/azure/subscription.bicep  •  infrastructure/azure/main.bicep

Microsoft/GitHub reference: Subscription-scope Bicep deployment  •  Azure resource locks

# 10. Prepare Azure SQL and the first administrator

Provisioning creates an empty Azure SQL database. The application will not become ready until the ordered schema, foundation reference data, runtime identity and bootstrap administrator are prepared.

## Choose the starting staff-data path

| Choice | Command switch | When to use |
| --- | --- | --- |
| Include supplied official curriculum staff seed | No exclusion switch | Only if database/HR owners confirm database/seed/005_seed_official_curriculum_staff.sql is approved, current and appropriate for production. |
| Do not include supplied staff seed | -ExcludeOfficialStaffData | Recommended if staff/organisation data will be imported from an approved current source or created through controlled onboarding. |

Do not confuse seeds The deployment list includes foundation configuration and may include the named official staff seed. It does not include the demo seed. Never run database/seed/002_seed_demo.sql, reset-localdb.ps1, fix-localdb.ps1 or test-data cleanup scripts against production.

## Apply every forward-only migration

.\scripts\apply-database.ps1 `
  -Server '<sql-server>.database.windows.net' `
  -Database 'ielevate' `
  -Authentication Entra `
  -ExcludeOfficialStaffData

Remove -ExcludeOfficialStaffData only after explicit approval. The script verifies SQL/Azure SQL compatibility, creates dbo.schema_migrations, applies its explicit list through 070_qa_action_workflow_and_inclusion_walks.sql, records SHA-256 checksums and skips already-applied entries. BaselineExistingDatabase is only for the documented legacy V1 case and must not be used on a fresh production database.

## Give the App Service managed identity runtime access

Connect to the ielevate database as the configured Entra SQL administrator. Use the exact web app name from the deployment output. The application calls a stored procedure as well as reading and writing tables, so include EXECUTE.

CREATE USER [<exact-web-app-name>] FROM EXTERNAL PROVIDER;
ALTER ROLE db_datareader ADD MEMBER [<exact-web-app-name>];
ALTER ROLE db_datawriter ADD MEMBER [<exact-web-app-name>];
GRANT EXECUTE TO [<exact-web-app-name>];

Do not grant db_owner, db_ddladmin or a server administrator role to the runtime identity. If CREATE USER reports a duplicate display name, stop and resolve it with the Entra/DBA team using an object-ID-safe method rather than granting another principal by mistake.

## Confirm the migration ledger

SELECT migration_key, checksum_sha256, applied_at
FROM dbo.schema_migrations
ORDER BY applied_at, migration_key;

Retain the result with the change record. An already-applied migration whose checksum later changes causes deployment to stop; the correct fix is a new migration, not editing history.

## Link the bootstrap administrator

The email must already match an active staff record. Obtain the person's Entra Object ID from the tenant; it is not either app client ID. The candidate known from development is harrybentley@oldham.ac.uk, but the product owner and identity team must confirm the intended production administrator and provide the correct object ID.

.\scripts\set-bootstrap-admin.ps1 `
  -Server '<sql-server>.database.windows.net' `
  -Database 'ielevate' `
  -Email 'harrybentley@oldham.ac.uk' `
  -TenantId '2ff33ca4-e942-419c-b5ca-e224a5167498' `
  -ObjectId '<person-entra-object-id>' `
  -Authentication Entra

The script links the Entra identity, assigns super_admin and global scope, and writes an audit entry in one transaction. After sign-in works, add a second permanent college administrator through the application and verify both accounts before removing any temporary elevation.

## Remove the temporary migration firewall rule

az sql server firewall-rule delete `
  --resource-group rg-ielevate-prod-uks `
  --server '<sql-server-name>' `
  --name TemporaryDeploymentAddress

Repository reference: scripts/apply-database.ps1  •  scripts/set-bootstrap-admin.ps1  •  database/migrations  •  database/seed/005_seed_official_curriculum_staff.sql

Microsoft/GitHub reference: Configure Entra authentication for Azure SQL  •  Managed identity database connection

# 11. Build and deploy the application

## Preferred release path: GitHub produces the package

- Configure the four non-secret repository variables listed in Section 4.

- Open GitHub Actions → Build Azure release → Run workflow on the approved tag/commit according to college policy.

- The workflow installs .NET 10 and Node 24, verifies the Entra scope relationship, runs the repository release gate and creates i-elevate-linux-x64.zip plus release.json and manifest.json.

- Download the workflow artifact within its 30-day retention period. Calculate and record its SHA-256. Attach the accepted files to the GitHub Release or the college's approved immutable release store.

- Have the deployment operator compare the downloaded checksum with the approved change record before deployment.

## Equivalent controlled local build

.\scripts\new-azure-release.ps1 `
  -EntraTenantId '2ff33ca4-e942-419c-b5ca-e224a5167498' `
  -EntraApiAudience 'f6d35a24-dc89-40b0-819a-69400ed2491d' `
  -EntraSpaClientId '40b00b7a-32b3-4a89-bac0-f016fd431d95' `
  -EntraApiScope 'api://f6d35a24-dc89-40b0-819a-69400ed2491d/access_as_user'

Do not pass -AllowDirty. Do not normally skip install or security audits. The script builds the production SPA for same-origin API access, runs tests and dependency audits, publishes linux-x64 and writes .artifacts/azure/i-elevate-linux-x64.zip.

## Deploy the verified ZIP

.\scripts\deploy-azure.ps1 `
  -ResourceGroupName 'rg-ielevate-prod-uks' `
  -WebAppName '<web-app-name-from-output>' `
  -PackagePath 'C:\ApprovedReleases\i-elevate-linux-x64.zip' `
  -ExpectedSubscriptionId 'acd523b9-54eb-4bbe-8776-fb761860c362'

The script checks the Azure CLI subscription, performs a clean ZIP deployment, restarts the app and polls /health/ready for up to five minutes. ZIP deployment does not rebuild the application in Azure; the uploaded package must already be complete.

## If readiness does not become healthy

- Do not keep redeploying. Open App Service → Log stream and Application Insights Failures; note the trace/time and protect any staff data shown.

- Check App Service Configuration for the connection string, tenant/audience and both data-protection URIs. Confirm Production and AllowDevelopmentUser=false.

- Check the managed identity exists in the ielevate database with reader, writer and EXECUTE permission.

- Check SQL networking and DNS. If using private endpoints, test VNet integration and private DNS from App Service diagnostics.

- Call /health/live. If live is 200 but ready is 503, focus on the database. If live fails, focus on startup/runtime/package/configuration.

Reject the old local ZIP The pre-existing .artifacts/azure package inspected on 25 August 2026 was generated from commit 993a4dde with workingTreeDirty=true. Its SHA-256 begins 3062E069… and it is not an approved production release. Rebuild from the clean accepted tag.

Repository reference: scripts/new-azure-release.ps1  •  scripts/deploy-azure.ps1  •  scripts/verify-v1.ps1  •  .github/workflows/release-azure.yml

Microsoft/GitHub reference: Azure Web App ZIP deploy  •  Deploy files to App Service

# 12. Complete DNS, HTTPS and sign-in

## Use the Azure address first

The Bicep output returns https://<web-app>.azurewebsites.net. Azure secures that hostname automatically. Add it temporarily to the Web SPA registration, test sign-in and complete the technical pilot before changing public DNS.

## Map the college hostname

- The application owner requests the final hostname from the DNS team, for example ielevate.oldham.ac.uk. Confirm it is the permanent staff address and record an owner for renewal and DNS changes.

- In App Service → Custom domains, add the hostname. Follow Azure's displayed verification record and create the required DNS CNAME/TXT records through the college DNS process.

- On Basic tier or higher, select an App Service Managed Certificate if it meets policy, or bind the college's approved certificate. Wait until the custom domain shows Secured.

- Test HTTPS, certificate chain, renewal ownership and HTTP-to-HTTPS redirection from a staff network and an approved external network if public access is intended.

## Update application settings for the permanent URL

az webapp config appsettings set `
  --resource-group rg-ielevate-prod-uks `
  --name '<web-app-name>' `
  --settings `
    'Messaging__ApplicationUrl=https://ielevate.oldham.ac.uk' `
    'Cors__AllowedOrigins__0=https://ielevate.oldham.ac.uk'

The deployed SPA uses window.location.origin and same-origin API calls, so a hostname change does not by itself require a rebuild. Keeping the application URL and allowed origin aligned avoids incorrect future links or cross-origin surprises. Restart and recheck readiness after changing settings.

## Finish the SPA redirect and consent

☐  Add the exact custom HTTPS origin to i-Elevate Web → Authentication → SPA redirect URIs.

☐  Sign in through the custom hostname. If AADSTS50011 appears, compare the redirect URI in the error with the registered origin character by character.

☐  Confirm admin consent is granted and the intended staff group/users are assigned if Assignment required is enabled.

☐  Confirm logout and a second sign-in work in a new private browser session.

☐  After the support team agrees, remove obsolete temporary Azure/localhost redirect URIs from the production registration.

Microsoft/GitHub reference: App Service custom domains  •  App Service certificates  •  Redirect URI best practices

# 13. Pilot, acceptance and go-live

A green health endpoint proves the service can start and reach SQL. It does not prove permissions, workflows, reports or recovery. Use named test users that mirror real roles and scopes, then remove or disable them and delete their test records before launch.

## Technical acceptance

☐  CI, release verification, API tests, frontend production build and dependency audits pass on the exact release commit.

☐  /health/live and /health/ready return HTTP 200 over the final hostname.

☐  Application Insights receives requests, dependencies, exceptions and trace IDs without tokens, request bodies or staff narrative.

☐  Managed identity reaches SQL, Blob Storage and Key Vault; no application database password or Storage account key exists.

☐  Budget, availability, 5xx, database-connectivity, capacity and backup alerts reach a monitored support channel.

☐  Temporary migration IP firewall access is removed; final network controls match the approved design.

☐  Point-in-time restore or the agreed recovery method is tested to a separate database and recorded.

## Role and scope acceptance

| Persona | Must be tested |
| --- | --- |
| Admin | Platform-wide administration, reporting, QA actions/removal rights and audit; cannot accidentally lose last-admin access. |
| Teaching & Learning | College-wide permitted workflows and QA configuration/correction, without Admin-only removal where designed. |
| Director | Only assigned faculty access plus permitted QA access. |
| Head of Faculty | Own faculty, relevant teams, QA actions and profile visibility; no other faculty leakage. |
| Programme Leader | Managed teams, own QA actions and staff records; no sibling-team leakage. |
| QA Staff | QA access only through the additive permission/review rules; no unrelated staff-development privilege. |
| Tutor/staff | Own profile, records and actions; no QA Hub unless explicitly entitled. |
| ALS leadership | Expected ALS-specific LIV/Learning Walk access and scoped reporting. |

## Functional acceptance

☐  Staff profile, badges and CPD records display correctly and exports open.

☐  Learning Walk, Work Scrutiny, LIV, probation and Elevate Learning Environment workflows save, submit and reopen only as designed.

☐  QA review setup, question tagging, activity evidence, all-team allocation, dashboard distributions/drill-down, closure, reports and actions work.

☐  Closed QA reviews lock evidence; action monitoring and staff-profile provenance are correct.

☐  Excel, PDF and Word reports supported by each process open correctly and contain only the viewer's permitted faculty/team data.

☐  Audit rows are written for tested mutations, corrections, removals, closures and reopen actions.

☐  Keyboard navigation, focus order, contrast, tablet layout and common staff browsers have no blocking issue.

## Pilot and launch sequence

- Pilot with the product owner, one administrator, Teaching & Learning, one Head of Faculty, one Programme Leader, one QA Staff user and one Tutor using realistic but clearly marked pilot records.

- Run the permission leakage tests from direct URLs and APIs, not only menus. Obtain formal acceptance from product, technical, data and service owners.

- Remove pilot/test accounts or data unless they are legitimate retained production records. Recheck dashboards and actions after cleanup.

- Open Entra assignment to the approved staff group in the agreed launch window. Publish the final URL and short staff guidance.

- Monitor sign-ins, 401/403/500 rates, SQL health and support contacts closely during the first day and first week. Record launch outcomes and any accepted defects.

Repository reference: docs/deployment/v1-readiness.md  •  tests/access-control

# 14. Operate the live service

## Minimum monitoring

| Signal | Suggested alert / review | First owner |
| --- | --- | --- |
| External availability | Application Insights availability test against /health/ready; alert on repeated failures from multiple locations. | Service desk / application support |
| HTTP 5xx | Alert on sustained count/rate and inspect correlated exceptions/traces. | Application support |
| Readiness / DB dependency | Alert on 503 and failed SQL dependency calls. | Application + DBA |
| App capacity | CPU, memory, response time, requests, restarts and health status. | Azure platform |
| SQL capacity | vCore/CPU, storage, sessions, failures, blocking/deadlocks and resume latency. | DBA |
| Backups | Verify configured retention and backup health; alert on policy failures. | DBA |
| Cost | Actual and forecast budget thresholds plus anomaly review. | Service owner / finance |
| Azure incidents | Service Health and Resource Health alerts for the subscription/resources. | Azure platform |

## Daily, weekly and monthly rhythm

| Frequency | Checks |
| --- | --- |
| Daily / alert driven | Availability, failed requests, sign-in failures, readiness, SQL connectivity, platform incidents and urgent support tickets. |
| Weekly | Error trends, slow operations, database/storage growth, failed messages if later enabled, outstanding incidents and planned changes. |
| Monthly | Cost vs budget, access/admin changes, runtime/dependency updates, backup retention, restore evidence, telemetry volume/retention and service KPIs. |
| Termly / quarterly | Role/scope access review, Entra assignment review, app owners, privileged roles, staff/org data quality, disaster-recovery exercise and privacy retention. |
| Annually | Full service review: DPIA, architecture, region, capacity, certificates, suppliers/licensing, RPO/RTO, support ownership and roadmap. |

## Azure SQL backup policy

Azure SQL automatically takes full, differential and log backups. New databases default to seven days of point-in-time retention; supported non-Basic tiers can be configured up to 35 days, and long-term retention can retain full backups for up to ten years. The college must set the values that meet its operational and data-retention needs, then rehearse restore.

Restore creates another database Point-in-time restore does not overwrite the existing database. Azure creates a new database. Validate the restored data and permissions before any controlled cutover. Never delete the original until the recovery owner signs off.

## Data-protection key continuity

- The key ring lives in the data-protection Blob container; the wrapping key lives in Key Vault.

- Blob/container soft delete is 30 days; Key Vault soft delete is 90 days with purge protection. Do not delete the Storage account, vault or key during an application rollback.

- Monitor access-denied failures. If the system-assigned identity is recreated by deleting/recreating the web app, its object ID changes and RBAC/database access must be reassigned.

## Support information every ticket should contain

- Time and timezone, user email, final URL and browser/device.

- What the user expected and what occurred; screenshot only after checking it contains no inappropriate staff data.

- HTTP status or visible message and the application's trace/correlation ID if shown.

- Whether the issue affects one person, one faculty/team or everyone.

- Recent release/configuration/Entra/network changes and health status.

Microsoft/GitHub reference: Application Insights availability  •  App Service health check  •  Azure SQL automated backups  •  Azure Service Health

# 15. Release updates safely

## Standard release flow

- Create a short-lived branch from the current protected main branch and implement the change with tests and, where needed, a new forward-only SQL migration.

- Open a pull request. CI must pass; an independent reviewer checks functionality, security, permission scope, migration safety and documentation.

- Merge through the protected branch, create an annotated release tag and run Build Azure release on that accepted source.

- Record release tag, full commit, package SHA-256, manifest, change approval, deployment operator, maintenance window and rollback package.

- Confirm a restorable database point/backup before applying any new migration. Run apply-database.ps1; do not edit an existing migration.

- Deploy the verified ZIP with deploy-azure.ps1, check readiness, run smoke tests and monitor errors/latency after release.

- Close the change only after the product owner or delegate confirms the intended user journey and no scope leakage.

## Package rollback and database reality

A previous ZIP can be redeployed to restore application files. Database migrations are not automatically reversed and may make older code incompatible. Every schema-changing release must state whether the previous application remains compatible. If it is not, the recovery plan is a tested database restore/cutover, not ad-hoc reverse SQL.

## Recommended production evolution

- Upgrade App Service to Standard or better and introduce a staging deployment slot if low-downtime releases are required. Deploy to staging, smoke test, then swap.

- Add a GitHub production Environment with required reviewers and Azure workload identity federation before automating deployment; avoid long-lived publish profiles.

- Add infrastructure validation/what-if to the controlled release process and review Bicep API versions periodically.

- Implement private networking in Bicep, not by undocumented portal drift, if the security decision requires it.

Repository reference: .github/workflows/ci.yml  •  .github/workflows/release-azure.yml  •  scripts/verify-v1.ps1

Microsoft/GitHub reference: App Service deployment best practices

# 16. Rollback, recovery and incidents

## Application-only rollback

- Declare the incident/change failure and stop further releases. Capture current health, error rate, release tag and database migration state.

- Confirm the retained previous ZIP checksum and whether it is compatible with the current database schema.

- Redeploy that ZIP using scripts/deploy-azure.ps1 with the same resource group, app name and expected subscription.

- Verify /health/ready, sign-in and the affected workflow. Continue monitoring and record the rollback in the audit/change record.

## Database recovery

- Define the required recovery point and freeze application writes if necessary. Preserve evidence and engage the DBA/service owner.

- Use Azure SQL point-in-time or long-term backup restore to create a new database. Do not overwrite/delete the live database.

- Validate schema_migrations, record counts, recent audit data, key workflows and permission/scoping in the restored database.

- Create the App Service managed-identity user and runtime grants in the restored database if they are not restored as expected; verify carefully.

- Change the App Service connection string only under an approved cutover, restart, check readiness and run acceptance smoke tests.

- Retain the old database until the recovery owner confirms success and the required forensic/retention period has passed.

## Loss of the web app identity

A system-assigned identity is tied to the web app. Recreating the app creates a new Entra principal. Re-run the Storage and Key Vault role assignments through Bicep, recreate the Azure SQL contained user for the new web-app name/object, and verify no stale principal retains access.

## Incident severity examples

| Condition | Immediate action |
| --- | --- |
| Possible staff-data disclosure or cross-scope access | Disable affected access or service as authorised, preserve logs, contact information governance/security, do not circulate exports. |
| All users receive 503 | Check /health/live vs /health/ready, App Service status, SQL networking/service health and recent changes. |
| Sign-in fails for all | Check Entra service health, SPA redirect URI, consent, API permission/scope, Conditional Access and tenant/audience settings. |
| One user receives 403 | Authentication probably succeeded; inspect active staff record, role, access scope, leadership/membership and review assignment. |
| Report contains unexpected faculty/team | Stop distribution, preserve the file securely, test direct API scope, engage product/security and treat as potential data incident. |

Microsoft/GitHub reference: Restore Azure SQL from backups

# 17. Security and privacy operating controls

## Access and identity

☐  At least two controlled administrators exist; emergency access is governed and monitored.

☐  Entra app owners, assignments, administrator consent and Conditional Access are reviewed on schedule.

☐  Application roles, leadership mappings, faculty/team scopes and QA Staff access are reviewed termly and when staff change role.

☐  Leavers are disabled in Entra and archived/disabled in i-Elevate according to the agreed process.

☐  Azure RBAC, SQL administrators and GitHub organisation access use least privilege and named accounts/groups.

## Data handling

- Treat staff profiles, performance/quality evidence, narrative comments, actions, audit history and exports as staff-confidential.

- Store production exports only in approved access-controlled locations. Delete working copies according to retention policy.

- Do not place screenshots, database exports or production logs containing personal data in GitHub issues, public tickets or this repository.

- Do not enable general evidence attachments until an approved storage, access, malware-scanning and retention design exists.

- Review the legal basis, privacy notice, subject-access process, retention and deletion rules with information governance before staff launch.

## Secrets and configuration

- No client secret belongs in the SPA. The API validates user tokens; the app uses managed identity for Azure services.

- Keep the SQL break-glass password in the approved enterprise secret/password vault and rotate it after setup and on personnel/process change.

- Never commit completed parameter/settings files, access tokens, certificates, database backups, release ZIPs or production reports.

- Review App Service settings access and activity logs. Treat environment configuration as production change-controlled data.

## Logging standard

- Collect request path, status, duration, dependency status, exception type, trace ID and operational user/account ID only where justified.

- Do not log bearer tokens, cookies, passwords, request/response bodies, staff reflections, QA narrative or exported report contents.

- Restrict telemetry access, set retention, test deletion/subject handling where applicable and monitor unusual query/export access.

Network approval must be explicit The current Bicep uses public endpoints with authentication/RBAC and a permissive SQL Azure-services firewall rule. If this does not meet policy, change and review the infrastructure-as-code before go-live. A portal-only network workaround creates undocumented drift and a fragile recovery path.

Repository reference: HANDOVER.md  •  .gitignore  •  docs/architecture/relationships-permissions-decisions.md

# 18. Troubleshooting guide

| Symptom | Likely area | Plain-English check |
| --- | --- | --- |
| AADSTS50011 reply URL error | SPA redirect | Register the exact window.location.origin value as an SPA redirect; remove typo/path/trailing-address mismatch. |
| Consent button disabled | Entra privilege | Use an authorised Cloud/Application Administrator or Privileged Role Administrator through college PAM; do not create a duplicate app. |
| 401 from API | Token/registration | Check browser requested the exact access_as_user scope and API validates the expected tenant/audience. |
| 403 from API | Application permission/scope | Check active staff record, role, faculty/team scope, leadership and review assignment. UI visibility is not proof. |
| /health/live 200, /health/ready 503 | Database | Check SQL networking, managed identity contained user, reader/writer/EXECUTE and connection settings. |
| App will not start | Production configuration | Check tenant, audience, SQL string and both data-protection settings. Production deliberately refuses incomplete protection. |
| Key Vault or Blob 403 | Managed identity/RBAC/network | Compare current web app principal with role assignments; check private DNS/firewall and allow RBAC propagation time. |
| ZIP deploy succeeds, site unhealthy | Package/runtime/startup | Check TLQS.Api.dll at ZIP root, linuxFxVersion .NET 10, startup command, logs and DB readiness. |
| First request slow | SQL serverless resume | Check whether Azure SQL paused; use retry/monitoring and decide whether serverless is appropriate. |
| SQL never pauses | Health traffic/session | Health check queries /health/ready every minute; inspect sessions and cost, then choose reliability vs pause intentionally. |
| New user sees onboarding | Expected first-use path | Confirm the tenant user is approved, selects the correct faculty/team/category and receives staff role; admin assigns leadership later. |
| Report is empty | Academic year/filter/scope | Check selected year, review state, faculty/team filters and server-calculated access; do not broaden scope just to make data appear. |
| Migration checksum error | Edited history | Stop. Restore the migration file from the accepted source and add a new forward-only migration for any new change. |

## Fast evidence commands

az webapp show -g rg-ielevate-prod-uks -n '<web-app>' `
  --query "{state:state,host:defaultHostName,identity:identity.principalId}"

az webapp config show -g rg-ielevate-prod-uks -n '<web-app>' `
  --query "{runtime:linuxFxVersion,health:healthCheckPath,alwaysOn:alwaysOn}"

Invoke-RestMethod 'https://<host>/health/live'
Invoke-RestMethod 'https://<host>/health/ready'

Protect troubleshooting output App settings, SQL results and logs can reveal environment details or staff information. Store diagnostic evidence only in the controlled incident/change record, redact it before sharing and never paste access tokens or passwords.

# 19. Formal handover pack

The handover is complete only when another authorised college team can build, deploy, operate and recover the service without the original developer's personal account or memory.

## Deliver together

☐  College-owned private GitHub repository with full history, protected main branch, at least two administrators and an accepted tagged release.

☐  Release ZIP, release.json, manifest.json and SHA-256 in the approved immutable release store/GitHub Release.

☐  This implementation guide plus the accepted production-readiness checklist and change record.

☐  Controlled environment register: tenant, subscription, resource group, resource names, URLs, Entra app/service-principal IDs, DNS, owners, support and escalation.

☐  Secret locations and recovery access—not secret values—including SQL break-glass credential custody and privileged access procedure.

☐  Database migration ledger, backup/retention policy, RPO/RTO, latest restore-test evidence and recovery owner/deputy.

☐  Monitoring dashboard, alert/action-group destinations, budget thresholds, service-health alerts and service-desk knowledge article.

☐  Accepted role/scope test evidence, pilot results, known issues, out-of-scope items and roadmap decisions.

## Handover demonstration

- A receiving maintainer checks out the tag on a clean machine and runs the release verification successfully.

- A receiving platform engineer explains the Bicep resources, costs, managed identity, public/private network decision and deployment outputs.

- A receiving DBA proves migration history, runtime permissions and a restore to a separate database.

- A receiving identity engineer demonstrates app ownership, permission consent, assignment, redirect URIs and Conditional Access.

- A receiving support analyst locates health, telemetry, alerts, trace IDs, rollback package and escalation contacts.

- The product owner signs that key user journeys and scope boundaries are accepted.

Avoid single-person dependency At least two permanent college staff should be able to administer GitHub, Azure, Entra and recovery. Named deputies must be able to activate the required access without relying on a personal account owned by the original developer.

Repository reference: HANDOVER.md  •  DEPLOYMENT-START-HERE.md  •  docs/deployment/v1-readiness.md

# Annex A. Known environment record

These identifiers were known when this guide was prepared. They are not secrets, but the controlled production environment register must verify them in Azure/Entra and add the generated resource names and owners.

| Item | Known value / state |
| --- | --- |
| Tenant ID | 2ff33ca4-e942-419c-b5ca-e224a5167498 |
| Azure subscription ID | acd523b9-54eb-4bbe-8776-fb761860c362 |
| Resource group | rg-ielevate-prod-uks — exists and was empty before provisioning |
| Region | UK South / uksouth |
| API app client ID | f6d35a24-dc89-40b0-819a-69400ed2491d |
| Web SPA client ID | 40b00b7a-32b3-4a89-bac0-f016fd431d95 |
| Delegated API scope | api://f6d35a24-dc89-40b0-819a-69400ed2491d/access_as_user |
| Current source remote | https://github.com/HBentley21299/teaching-learning-quality-system.git — transfer to college-owned private organisation |
| Inspected source commit | a4b0d0b9f747d2e31e2cf1a4888132928a369812 (a4b0d0b9), main, clean at inspection |
| Candidate bootstrap email | harrybentley@oldham.ac.uk — confirm production owner and obtain person's Entra Object ID |
| Final production hostname | Outstanding — agree with DNS/service owner before final SPA redirect |
| Tenant-wide consent | Outstanding at preparation; requires authorised Entra administrator |
| Azure resources | Not provisioned at preparation; Bicep deployment creates billable resources |
| Existing local Azure ZIP | Rejected for production: generated from earlier dirty commit 993a4dde; rebuild from clean approved tag |

## Fields to add after provisioning

☐  Subscription display name, billing scope/cost centre and budget amount/recipients.

☐  Subscription deployment name and timestamp.

☐  Generated Web App, App Service plan, SQL server, Storage, Key Vault, Application Insights and Log Analytics names/resource IDs.

☐  Web app managed-identity object ID, SQL contained user and RBAC evidence.

☐  Azure default URL, final custom URL, DNS records and certificate owner/renewal method.

☐  Entra app owners, enterprise application assignment groups, consent approver and Conditional Access policy names.

☐  SQL administrator, backup retention/redundancy/LTR, RPO/RTO and restore-test date.

☐  Service owner/deputy, product owner, support queue, escalation contacts and maintenance window.

# Annex B. Azure command sheet

Replace angle-bracket placeholders. Run from the repository root in PowerShell. Read each command before execution and keep secret-bearing values out of command history where the college's approved tooling supports a safer method.

## 1 — Login and verify context

az login --tenant 2ff33ca4-e942-419c-b5ca-e224a5167498
az account set --subscription acd523b9-54eb-4bbe-8776-fb761860c362
az account show -o table

## 2 — Compile, validate, preview and create

az bicep build --file .\infrastructure\azure\subscription.bicep
az deployment sub validate --name ielevate-prod-validate-<date> `
  --location uksouth --template-file .\infrastructure\azure\subscription.bicep `
  --parameters "@C:\Secure\i-elevate\subscription.parameters.prod.json"
az deployment sub what-if --name ielevate-prod-whatif-<date> `
  --location uksouth --template-file .\infrastructure\azure\subscription.bicep `
  --parameters "@C:\Secure\i-elevate\subscription.parameters.prod.json"
az deployment sub create --name ielevate-prod-<date> `
  --location uksouth --template-file .\infrastructure\azure\subscription.bicep `
  --parameters "@C:\Secure\i-elevate\subscription.parameters.prod.json"

## 3 — Database migrations and bootstrap

.\scripts\apply-database.ps1 -Server '<server>.database.windows.net' `
  -Database ielevate -Authentication Entra -ExcludeOfficialStaffData
.\scripts\set-bootstrap-admin.ps1 -Server '<server>.database.windows.net' `
  -Database ielevate -Email '<approved-admin@oldham.ac.uk>' `
  -TenantId '2ff33ca4-e942-419c-b5ca-e224a5167498' `
  -ObjectId '<person-object-id>' -Authentication Entra

## 4 — Build and deploy

.\scripts\new-azure-release.ps1 `
  -EntraTenantId '2ff33ca4-e942-419c-b5ca-e224a5167498' `
  -EntraApiAudience 'f6d35a24-dc89-40b0-819a-69400ed2491d' `
  -EntraSpaClientId '40b00b7a-32b3-4a89-bac0-f016fd431d95' `
  -EntraApiScope 'api://f6d35a24-dc89-40b0-819a-69400ed2491d/access_as_user'
.\scripts\deploy-azure.ps1 -ResourceGroupName rg-ielevate-prod-uks `
  -WebAppName '<web-app>' -ExpectedSubscriptionId `
  'acd523b9-54eb-4bbe-8776-fb761860c362'

## 5 — Verify

Invoke-RestMethod 'https://<host>/health/live'
Invoke-RestMethod 'https://<host>/health/ready'
az webapp show -g rg-ielevate-prod-uks -n '<web-app>' -o table
az webapp log tail -g rg-ielevate-prod-uks -n '<web-app>'

## 6 — Remove temporary SQL migration access

az sql server firewall-rule delete -g rg-ielevate-prod-uks `
  -s '<sql-server-name>' -n TemporaryDeploymentAddress

# Annex C. Repository reference map

| Path | Why the implementer needs it |
| --- | --- |
| DEPLOYMENT-START-HERE.md | Short production sequence and entry point. |
| HANDOVER.md | Ownership, transfer, deliverables and known-state record. |
| infrastructure/azure/subscription.bicep | Subscription-level resource-group creation and main module invocation. |
| infrastructure/azure/main.bicep | Exact App Service, SQL, Storage, Key Vault, telemetry, settings, identity and RBAC definition. |
| infrastructure/azure/subscription.parameters.example.json | Placeholder-only parameter schema; copy outside source control. |
| scripts/verify-v1.ps1 | Full release gate: clean tree, builds, tests, audits, metadata and manifests. |
| scripts/new-azure-release.ps1 | Builds the same-origin Linux production ZIP with Entra identifiers embedded in the SPA. |
| scripts/deploy-azure.ps1 | Checks subscription, ZIP deploys, restarts and polls readiness. |
| scripts/apply-database.ps1 | Explicit ordered deployment list through migration 070 with checksum ledger. |
| scripts/set-bootstrap-admin.ps1 | Links the first Entra identity to an active staff record and grants audited super-admin/global access. |
| database/migrations | Forward-only schema and feature history. Never edit an applied file. |
| database/seed/001_seed_foundation.sql | Required platform configuration/reference foundation. |
| database/seed/005_seed_official_curriculum_staff.sql | Optional production staff starting dataset; include only when approved/current. |
| database/seed/002_seed_demo.sql | Demo data; never run in production. |
| .github/workflows/ci.yml | Build/test/audit/compile checks on main and pull requests. |
| .github/workflows/release-azure.yml | Manual reproducible Linux release artifact workflow. |
| docs/deployment/v1-readiness.md | Mandatory acceptance checklist. |
| docs/deployment/on-premises-operations.md | Windows/IIS and on-campus SQL contingency operations. |
| docs/architecture/overview.md | System architecture and module boundaries. |
| docs/architecture/relationships-permissions-decisions.md | Role, relationship and scope design decisions. |
| apps/web/src/services/auth.ts | MSAL SPA configuration; redirect uses window.location.origin and sessionStorage. |
| apps/api/src/TLQS.Api/Program.cs | Production authentication, database, data protection, health and middleware wiring. |

# Annex D. On-campus IIS and SQL Server hosting

Alternative, not a hybrid add-on Choose this route only through an explicit hosting decision. It replaces Azure App Service and Azure SQL with Windows IIS and on-campus SQL Server. Do not mix Azure Linux packages/settings with Windows/IIS packages/settings.

## Supported production shape

- One supported Windows Server running IIS serves the React UI and ASP.NET Core API from one HTTPS hostname.

- One on-campus Microsoft SQL Server 2017 or later database with compatibility level 140 or later stores all application data.

- A group Managed Service Account (gMSA) runs the IIS application pool and uses Windows Integrated Security to SQL; no database password is stored in the app.

- Microsoft Entra app registrations remain required for staff browser sign-in. The production SPA must be built with the same tenant, API and Web IDs.

- Versioned release folders under C:\inetpub\i-elevate\releases allow application-file rollback. Data-protection keys live outside releases and are protected by Windows DPAPI.

## One-time server and SQL preparation

☐  Patch and harden supported Windows Server; install IIS Management Tools, required IIS modules and the current .NET 10 Hosting Bundle/ASP.NET Core Module. Restart IIS after installation.

☐  Create internal/external DNS as approved, obtain a trusted server certificate, create the IIS HTTPS binding and require HTTPS.

☐  Create gMSA COLLEGE\iElevateServiceAccount$ (or approved name), permit the IIS server to retrieve its managed password and configure the i-Elevate application pool to run as that identity.

☐  Create SQL database iElevate, set compatibility level at least 140, configure encryption with a trusted SQL certificate and allow TCP connectivity from the IIS server.

☐  Create the Windows login for the gMSA on SQL Server. The repository grant script then creates the database user, adds datareader/datawriter and grants EXECUTE.

☐  Create IIS site and application pool named i-Elevate. The deployment script expects them to exist; it changes the site's physical path to the new versioned release.

☐  Create C:\ProgramData\i-Elevate\DataProtection-Keys outside the release tree and include it in the protected server backup plan.

## Grant database runtime access

-- DBA runs once at server level if the login does not exist:
CREATE LOGIN [COLLEGE\iElevateServiceAccount$] FROM WINDOWS;

# Then run from the repository root as an authorised Windows DBA:
.\scripts\grant-on-premises-database-access.ps1 `
  -Server '<sql-server>\<instance>' -Database 'iElevate' `
  -RuntimePrincipal 'COLLEGE\iElevateServiceAccount$'

## Create the protected settings file

Copy-Item .\deployment.settings.example.psd1 `
  .\deployment.settings.psd1

Complete SiteName, AppPoolName, RuntimePrincipal, InstallRoot, ApplicationUrl, SQL server/database/encrypted Integrated Security connection string, DataProtectionKeyPath, the four Entra values, bootstrap admin email/object ID and IncludeOfficialStaffData. The completed file is Git-ignored; keep the operational copy under controlled access.

## Build the Windows package

.\scripts\new-on-premises-release.ps1 `
  -SettingsPath .\deployment.settings.psd1

The output is a win-x64 i-elevate-<commit>-win-x64.zip. Build from a clean approved commit and retain its SHA-256, manifest and release metadata.

## Initial and later deployment

# Initial deployment to a new empty database:
.\scripts\deploy-on-premises.ps1 `
  -SettingsPath .\deployment.settings.psd1 `
  -PackagePath 'C:\ApprovedReleases\i-elevate-<commit>-win-x64.zip' `
  -InitialDeployment

# Later release after the DBA confirms a restorable backup:
.\scripts\deploy-on-premises.ps1 `
  -SettingsPath .\deployment.settings.psd1 `
  -PackagePath 'C:\ApprovedReleases\i-elevate-<commit>-win-x64.zip' `
  -DatabaseBackupConfirmed

The script validates HTTPS and encrypted Integrated Security, applies migrations/bootstrap unless skipped, extracts a new release, writes appsettings.Production.json, grants filesystem ACLs, switches IIS and checks /health/ready. If startup fails it switches IIS back, but database migrations are never reversed.

## Application rollback

.\scripts\rollback-on-premises.ps1 `
  -SettingsPath .\deployment.settings.psd1 `
  -ReleasePath 'C:\inetpub\i-elevate\releases\release-<timestamp>'

## On-campus backup and recovery

- Agree RPO/RTO. Use full, differential and—under full recovery model—transaction-log backups. Monitor every backup job and perform scheduled restores to another database/server.

- Back up IIS configuration/certificate information, controlled deployment settings, current/previous packages/manifests and the data-protection key directory.

- Machine-scoped DPAPI is tied to the Windows server. A rebuild on another server can require re-entry of protected messaging secrets; rehearse the exact recovery path.

- Collect Windows Event Log, IIS access/error logs and application console logs. Alert on readiness, 500s, app-pool stops/recycles, SQL failures/blocking/deadlocks/capacity and missed backups.

## Scale-out warning

A second IIS server cannot safely share machine-scoped DPAPI keys as supplied. Before scale-out, introduce a shared protected key repository using an approved certificate, place servers behind an approved load balancer and retest session/data protection and deployment switching.

Repository reference: deployment.settings.example.psd1  •  scripts/new-on-premises-release.ps1  •  scripts/deploy-on-premises.ps1  •  scripts/rollback-on-premises.ps1  •  docs/deployment/on-premises-operations.md

Microsoft/GitHub reference: ASP.NET Core Module for IIS  •  Secure gMSA guidance  •  SQL Server full backups

# Annex E. Local development only

Not a staff hosting option SQL Server LocalDB and the Vite development server are for one developer workstation. They do not provide production identity, resilience, backup, support or multi-user hosting.

## Prerequisites and start

.\scripts\check-prerequisites.ps1
.\scripts\start-local.ps1
# Browse http://127.0.0.1:5173
.\scripts\stop-local.ps1

- Use -SkipDatabase only when the local database is already prepared.

- Use -ResetDatabase only when deliberately replacing local development data. It is destructive to that local database.

- Development authentication and local password accounts must never be enabled in Production.

- Never copy a LocalDB .mdf, test account, demo seed, local export or browser token into the production environment.

Repository reference: README.md  •  scripts/start-local.ps1  •  scripts/stop-local.ps1  •  apps/api/src/TLQS.Api/appsettings.Development.json

# Annex F. Go-live sign-off checklist

## Governance and ownership

☐  Product, technical, data, Azure, Entra, DBA and service/support owners and deputies are named.

☐  Private college GitHub repository, protected main branch and approved tag are in place.

☐  Cost estimate, cost centre, budget/forecast alerts and region approval are recorded.

☐  DPIA/information-governance, retention and staff privacy decisions are accepted.

## Platform and identity

☐  Bicep validate and what-if were reviewed; deployment outputs and resource inventory are recorded.

☐  Network/public endpoint decision is accepted and implemented in code; temporary SQL IP access is removed.

☐  HTTPS, custom domain, certificate and exact SPA redirect are verified.

☐  API scope, SPA permission, administrator consent, assignment and Conditional Access are verified.

☐  Managed identity RBAC and SQL least privilege are evidenced.

## Data and release

☐  Staff seed decision is recorded; no demo/reset/test data was applied to production.

☐  All migrations through the release list are present in dbo.schema_migrations with accepted checksums.

☐  Bootstrap administrator and a deputy are verified; no unsupported temporary admin remains.

☐  Exact release commit/tag, ZIP, manifest and SHA-256 are retained.

☐  /health/live and /health/ready are HTTP 200 on the final URL.

## Acceptance and operations

☐  All role and faculty/team boundaries, direct URLs/APIs and report exports are tested with no leakage.

☐  Core and QA workflows, actions, audit and supported reports are accepted.

☐  Pilot/test accounts and records are removed or legitimately retained and labelled.

☐  Availability, errors, database, capacity, cost, backups and Service Health alerts reach monitored owners.

☐  Backup retention and a restore drill meet the agreed RPO/RTO.

☐  Service desk, incident, release, rollback and escalation runbooks are live.

☐  Product, technical, information-governance and service owners have signed go-live.

# Annex G. Plain-English glossary

| Term | Meaning in this implementation |
| --- | --- |
| App Service | Azure's managed web hosting. It runs the .NET API and serves the compiled React interface. |
| Azure SQL Database | Managed Microsoft SQL database service holding i-Elevate's production records. |
| Bicep | Human-readable Azure infrastructure-as-code. It declares what Azure resources and settings should exist. |
| Client ID | Public identifier for an Entra application registration. It is not a password. |
| Managed identity | An Azure-managed machine identity for the web app, avoiding stored service credentials. |
| Microsoft Entra ID | The college identity platform formerly called Azure Active Directory. |
| Migration | An ordered forward-only SQL script that changes or seeds the application database. |
| Object ID | Entra's identifier for a particular user, group or service principal. Do not confuse it with an app client ID. |
| Private endpoint | A private IP in an Azure virtual network that reaches a managed Azure service without public data-plane access. |
| RPO | Recovery Point Objective: how much recent data loss the service can tolerate after a serious incident. |
| RTO | Recovery Time Objective: how long restoring an acceptable service can take. |
| Scope | The faculty, team, self or global boundary that limits what application records a user can access. |
| SPA | Single-page application: the React interface running in the browser. |
| Tenant | The college's Microsoft Entra directory boundary. |
| TLS/HTTPS | Encrypted connection between browser/service endpoints. |
| What-if | Azure preview showing expected infrastructure changes before they are applied. |
| ZIP deployment | Uploading an already-built package to App Service; Azure does not compile it again. |

# Annex H. External references

Official sources checked 25 August 2026. Microsoft and GitHub update their services; re-check the linked pages immediately before implementation.

Deploy Bicep files with Azure CLI

Subscription-scope Bicep deployments

Azure Web App ZIP deployment

App Service deployment best practices and slots

App Service health check

App Service custom domain

App Service certificates

App Service private endpoints

Managed identities overview

App Service managed identity to Azure database

Configure Entra authentication for Azure SQL

Azure SQL firewall rules

Azure SQL serverless

Azure SQL automated backups

Restore Azure SQL from backups

Azure Storage network security

Secure Azure Key Vault

ASP.NET Core Data Protection key storage

Expose a protected API scope

SPA redirect URI practices

Grant tenant-wide admin consent

Microsoft Entra Conditional Access

Azure Cost Management budgets

Application Insights availability tests

Azure Resource locks

ASP.NET Core Module for IIS

Secure group managed service accounts

SQL Server full database backups

Transfer GitHub work to an organisation

GitHub repository rulesets

## Final implementation note

The definitive behaviour is the accepted repository commit plus its migration ledger and deployed configuration. If this guide conflicts with a later reviewed code change, stop, update the guide through change control and re-run acceptance. Do not silently work around the difference in the portal or database.